## Slide 1: Time to resolve Design Issues

## Slide 2: Disclamer
Due to the engineering meeting last week I have not had time to coordinate this material with Tim or the L3 Managers.
  Use this as a general guide but not as concrete numbers. We are revising the schedule now and will hopefully have better dated in January

## Slide 3: Hard Deadlines
The DOE CD2/3c review is October 2019.
  We must be under EVMS (US) 6 months prior to this. And the Review cycle will start in April of 2019.
  Realistically no significant changes will be possible to the first detector module after November of 2018.
  One must foresee that due to the prototype activities some changes are necessary and one must leave time for this.
  Both detector 1 and 2 will be fixed at CD2/3c.
However any major change to the configuration after the start of production of the ProtoDUNE detector would either add to the experiment’s risk by installing non-fully tested elements or require a second run of ProtoDUNE.
  The project intends to plan a second protoDUNE run just in case the collaboration decides to proceed with this..

## Slide 4: Responsibility
If the working groups show that some aspect of the detector design negatively impacts science then DUNE as a whole will need to work to make changes to improve the design.
  Changes can increase detector cost, require re-design (with cost), and will produce delays. There must be sufficient funding at CD2/3c to construct the detectors. There will always be a cost benefit analysis.
The sooner any changes are known the easier they will be to implement.
We want to remain open to improving the detector.

## Slide 5: Some general short term considerations
APA Frame
The frame design is well advanced now.
  Dimensional changes require re-design
    Changing wire pitch would require evaluating the impact of the higher stresses before understanding how much time and effort is needed to affect the change.
This would probably cause a 6 month delay in ProtoDUNE now and cost probably 500k.
  Need input from L3 managers to refine the impacts.

## Slide 6: Some general short term considerations
APA continued
Changing wire pitch and angle
  The wire guides, winding pattern, and design of the front end electronics changes if the pitch and angle change.
  Design of the FEMB will start in January. It is planned to be doing first winding tests of a dummy frame in Spring.
  Changes in pitch and angle will have increasing impact on cost and schedule after Christmas (assume the frame does not need strengthened)
  I need input from the managers but simulation, redesign, re-tooling would probably cause a few months delay now and six months after spring. Cost impacts after Spring would be on the 1-2 million dollar level. Schedule delay will be 6 months plus elapsed time.

## Slide 7: Photon Detector
The interface to the APA needs to be defined at Christmas to keep on track.
  Changes after this could have the same impact as changes to the frame.
  The photon coverage would be highest priority.
Due to cost limitations work on the photon backend readout is not progressing this year.
Changes to the requirements for the backend readout should be known by late Spring so work can be planned for Fall. One year solid work minimum should be foreseen to make and test the backend readout for the photon system.
With the parallel development of SBND on could consider changing technology after ProtoDUNE for the detector number 1. However a risk analysis of this should be performed to understand possible implications.

## Slide 8: DAQ
The DAQ software including event builder, run control, slow control will require roughly one year if substantial changes from the 35t are to be made.
Hardware changes to backend readout (TPC and Photon) and timing would need longer to implement and test.
  We have not worked through when this needs to begin.

## Slide 9: Computing
Computing at CERN can become critical path and should not be forgotten.
  We need to be sure the data needed to select/design the optimum detector is collected.

## Slide 10: ProtoDUNE Data
If data is needed to verify the detector performance then this group should be sure it will be collected in ProtoDUNE.
Beam delivery to the cryostat must be resolved soon.
Are other inputs needed?

## Slide 11: Comments?