## Slide 1
VARIANCES Favorable is Positive, Unfavorable is Negative
Cost Variance CV = BCWP - ACWP CV % = (CV / BCWP) *100
Schedule Variance SV = BCWP - BCWS SV % = (SV / BCWS) *100
Variance at Completion VAC = BAC - EAC
OVERALL STATUS
% Schedule = (BCWScum /BAC) * 100
% Complete = (BCWPcum /BAC) * 100
% Spent = (ACWPcum/BAC) * 100
Cost Performance Index (CPI) = BCWP / ACWP Favorable is > 1.0, Unfavorable is < 1.0
Schedule Performance Index (SPI) = BCWP / BCWS Favorable is > 1.0, Unfavorable is < 1.0
DoD TRIPWIRE METRICS
BASELINE EXECUTION INDEX (BEI, A Schedule Metric) BEI = Tasks with Actual Finish Date / (# of Baseline Tasks Scheduled to Finish Prior to Status Date + Tasks Missing Baseline Start or Finish Date)
CRITICAL PATH LENGTH INDEX (CPLI, A Schedule Metric) CPLI = (CP Length (Time Now To Contract End)) + Total Float (To Contract End Baseline Finish) / CP Length
Hit / Miss = Month’s Tasks Completed ON or AHEAD / Month’s Tasks Scheduled to Complete
INDEPENDENT ESTIMATE AT COMPLETION (EAC) = Actuals to Date + [(Remaining Work) / (Performance Factor)]
EAC CPI = ACWPcum + [(BAC - BCWPcum) / CPIcum ] = BAC / CPIcum
EAC Composite = ACWPcum + [(BAC - BCWPcum) / (CPIcum * SPIcum)]
TO COMPLETE PERFORMANCE INDEX (TCPI)
TCPI EAC = Work Remaining / Cost Remaining = (BAC - BCWPcum) /(EAC - ACWPcum)
TCPI BAC = Work Remaining / Budget Remaining = (BAC - BCWPcum) /(BAC - ACWPcum)
EVMS Gold Card
Baseline Execution Index (BEI) – From IMS
  Cum index less than .95
Schedule Performance Index (SPI) – From IPMR
  Cum index less than .95
Critical Path Length Index (CPLI) – From IMS
  Cum index less than .95
Cost Performance Index (CPI) – – From IPMR
  Cum index less than .95
To Complete Performance Index (TCPI) – – From IPMR
  CPI to TCPI delta of 10%
Contract Mods – ACO, PCO
  Contract Mods to Original Base value of 10%
PMB Revisions – From IPMR
  Changes to Monthly Time-Phased PMB value of 5%
DoD TRIPWIRE METRICS
EVM Solutions, Inc.
9070 Lakes Blvd.
West Palm Beach FL 33412
561.694.1646 jwrisley.wpb@hotmail.com

## Slide 2: EVMS Acronyms
ACWP Actual Cost of Work Performed {Actual Cost or AC]
AUW Authorized Unpriced Work (contractually authorized, but not yet negotiated)
BAC Budget at Completion = Σ BCWS = Sum of Budgeted Cost of Work Scheduled
BCWP Budgeted Cost for Work Performed [Earned Value or EV]
BCWR Budgeted Cost for Work Remaining
BCWS Budgeted Cost for Work Scheduled [Planned Value or PV]
CA Control Account (includes AUW) = WPs + PPs
CAA Control Account Authorization
CAM Control Account Manager
CBB Contract Budget Base = PMB + MR
CP Contract Price = Contract Target Cost + profit/fee
CPI Cost Performance Index
CV Cost Variance
EAC Estimate At-Completion
IBR Integrated Baseline Review
IEAC Independent Estimate At-Completion
LOE Level-of-Effort
MR Management Reserve is held by contractor (Contingency is held by DOE)
OBS Organizational Breakdown Structure
OTB Over-Target Baseline
PB Performance Baseline (TPC) = CBB + Contingency + DOE OPC
PMB Performance Measurement Baseline = CAs + UB + SLPPs
PP Planning Package (far-term activities within a CA)
SLP Summary Level Planning
SPI Schedule Performance Index
UB Undistributed Budget (activities not yet distributed to CA)
TEC Total Estimated Cost
TPC Total Project Cost
VAC Variance At-Completion
WAD Work Authorization Document
WBS Work Breakdown Structure
WP Work Package (near-term, detail-planned activities within a CA)
CBB
Contingency
TPC
PB
(TPC)
Contingency
(DOE Held)
Contract Price
(CTC+Profit)
DOE
Other Direct Costs
MR
(Contractor Held)
PMB
(Includes AUW)
Profit
Summary Level Planning
Control Accounts
UB
Work Packages
Planning Packages