## Slide 1: Solution
Exercise 1

## Slide 2
J
J
A
S
O
N
D
J
F
M
40
40
60
80
80
100
80
60
60
100
20
20
30
30
30
30
20
20
4
4
6
8
8
10
8
6
40
40
60
80
80
60
60
60
20
20
20
20
20
20
20
20
20
20
Month
Cum
Time Now
BAC | Mo. | Cum
540 | 0 | 140
160 | 0 | 0
200 | 10 | 30
54 | 0 | 14
300 | 30 | 60
180 | 90 | 90
200 | 20 | 100
1634 | 150 | 434
Control Account Plan
WP 1: M/S
WP 2: 0/100
WP 3: % Comp
WP 4: Apport.
WP 5: % Comp
WP 6: 50/50
WP 7: LOE
64 64 106 168 298 380 278 196 40 40
298 150 300 -148 -150
700 434 650 -266 -216
BCWS BCWP ACWP SV CV

## Slide 3: Solution
Exercise 2

## Slide 4: Case 2 Solution
1. SV and CV:
Amount %
SV (7,858) (9.1)
CV (12,647) (16)
2. At Completion Variance:
To PMB
PMB = BACCBB – MR = 292,420 – 11,982 = 280,438
At Completion Variance = BAC – EAC = 280,438 – 281,960 = (1,522)
To CBB
At Completion = BAC – EAC = 292,420 – 281,960 = 10,460
Note: 10,460 – MR = 10,460 – 11,982 = (1,522)
Notes: Copyright © 2000 Performance Management Associates, Inc. All Rights Reserved
4

## Slide 5: Case 2 Solution (cont.)
3. SPI/CPI:
SPI =
BCWP
BCWS
=
78,875
86,733
=
.91
CPI =
BCWP
ACWP
=
78,875
91,522
=
.86
4. Percent Complete:
a. % Complete of PMB:
BCWP
BACPMB
=
78,875
280,438
=
.28
b. % Complete of CBB:
BCWP
BACCBB
=
78,875
292,420
=
.27
c. % Spent of EAC:
ACWP
EAC
=
91,522
281,960
=
.32
Notes: Copyright © 2000 Performance Management Associates, Inc. All Rights Reserved
5

## Slide 6: Case 2 Solution (cont.)
5. Efficiency:
TCPI =
BAC – BCWP
EAC – ACWP
=
280,438 – 78,875
281,960 – 91,522
=
1.06
=
201,563
190,438
a. PMB:
b. The calculation of a TCPI using the CBB would be meaningless because the existing EAC assumes no further distribution of MR, but the BAC of the CBB does assume such a distribution. Thus, the numerator and denominator of the TCPI formula would be based on two different conditions.
Notes: Copyright © 2000 Performance Management Associates, Inc. All Rights Reserved
6

## Slide 7: Case 2 Solution (cont.)
6. EAC:
IEAC =
BAC
CPI
–
=
326,091@PMB
TOTAL =
292,420
.86
=
340,023@CBB
280,438
.86
a.
IEAC =
BCWR
CPI x SPI
=
349,078
ACWP
b.
+
IEACPMB =
201,563
.86 x .91
91,522
+
=
364,388
IEACCBB =
213,545
.7826
91,522
+
Notes: Copyright © 2000 Performance Management Associates, Inc. All Rights Reserved
7

## Slide 8: Case 2 Solution (cont.)
6. EAC cont’d:
IEAC =
c.
IEAC =
BCWR
(.2)SPI + (.8)CPI
=
317,997
ACWP
d.
+
IEACPMB =
201,563
.89
91,522
+
=
331,460
IEACCBB =
213,545
.89
91,522
+
BCWR
CPI3
ACWP
+
=
323,204
IEACPMB =
201,563
(.2)(.91) + (.8)(.86)
91,522
+
=
336,976
IEACCBB =
213,545
.87
91,522
+
e.
IEACPMBAVG = $331.1
IEACCBBAVG = $345.3
Notes: Copyright © 2000 Performance Management Associates, Inc. All Rights Reserved
8

## Slide 9: Case 2 Solution (cont.)
Note: We have provided calculation of the IEAC based upon no further distribution of management reserve (IEACPMB) and based upon full distribution of the MR (IEACCBB). This provides you with the full range of possible IEACs.
The way an IEAC is typically calculated is to base the calculation on the PMB and then add in your own assessment of how much more management reserve will be distributed.
Notes: Copyright © 2000 Performance Management Associates, Inc. All Rights Reserved
9

## Slide 10: Case 2 Solution (cont.)
7. a. Months Ahead/Behind = SV/BCWS Ave per month
= -7858
13333
= .56 Months behind
7.b. Projected At-Completion Ahead/Behind =
BAC-BAC/SPI
Ave Monthly BCWS =
= 2.08 Months behind at-completion
280,438 – (280,438/.91)
13333
Notes: Copyright © 2000 Performance Management Associates, Inc. All Rights Reserved
10